## Roadmap
Placement Tracker: Build Roadmap
Edit the blue cells (status, session estimates, assumptions); everything else recalculates.
Assumptions
Hours per session |  | 2
Sessions per week (faster pace) |  | 5
Sessions per week (slower pace) |  | 4
# | Module | Status | Min sessions | Max sessions | Needed for v1 launch? | Notes
1 | Big picture | Done |  |  | Yes
2 | Docker | Done |  |  | Yes
3 | Databases | Done |  |  | Yes
4 | APIs (FastAPI) | Next | 1 | 2 | Yes
5 | Auth & security (OTP, JWT, roles) | Not started | 2 | 3 | Yes | Launch needs admin login only; student accounts can wait for Module 10 (saves 1-2 sessions)
6 | Placement service (drives, rounds, stats, admin) | Not started | 3 | 4 | Yes
7 | Events (Redis Streams, outbox) | Not started | 2 | 2 | Yes
8 | Frontend (Next.js pages) | Not started | 3 | 4 | Yes
9 | Deployment (GCP, HTTPS, backups) | Not started | 2 | 2 | Yes | Milestone: live site with 2025-26 archive and 2026-27 live board
10 | Community + realtime + DMs | Not started | 4 | 5 | No
11 | Scale & ops (k3s, CI/CD, monitoring) | Not started | 2 | 3 | No
Summary
Modules done |  | 3
Total modules |  | 11
Progress |  | 27.27%
Remaining sessions (min) |  | 19
Remaining sessions (max) |  | 25
Remaining hours (min) |  | 38
Remaining hours (max) |  | 50
Remaining weeks (best case) |  | 3.8
Remaining weeks (slower case) |  | 6.25
Sessions to v1 launch (min) |  | 13
Sessions to v1 launch (max) |  | 17
Weeks to v1 launch (best case) |  | 2.6
Weeks to v1 launch (slower case) |  | 4.25
Note: the v1 launch figures assume full Module 5; doing admin-only login for launch saves 1-2 sessions.
Note on C5: From the roadmap discussion: a session is ~2 hours of focused work
Note on C6: From the roadmap discussion: 4-5 sessions a week
Note on C7: From the roadmap discussion: 4-5 sessions a week